## Summary
AIlit Master Build Tracker
Purpose | Track the compounding knowledge and maintenance backlog before splitting implementation across worktrees.
Current planning artifacts
Requirements doc | docs/brainstorms/ailit-compounding-knowledge-requirements.md
Implementation plan | docs/plans/ailit-compounding-knowledge-plan.md
KPI | Value | Phase | Focus
Total backlog items |  | Phase 1 | Artifact model, templates, docs
Done |  | Phase 2 | Solution registry and validation
In progress |  | Phase 3 | Capture and promotion commands
Planned |  | Phase 4 | Prepare integration and auditability
P0 items |  | Phase 5 | Governance, freshness, org rollout
Org-level items
|  | Execution note | Use the backlog sheet as the working queue. Split lanes by docs, registry, runtime, governance, and QA.

## Backlog
ID | Epic | Workstream | Task | Why It Matters | Priority | Status | Phase | Knowledge Level | Depends On | Target Artifact | Suggested Owner | Notes
BK-001 | Planning | Requirements | Create compounding knowledge requirements document | Capture the problem, scope, and success criteria before implementation. | P0 | Done | Phase 0 | Org |  | docs/brainstorms/ailit-compounding-knowledge-requirements.md | Platform | Completed on 2026-05-06.
BK-002 | Planning | Implementation Plan | Create compounding knowledge implementation plan | Define the phased delivery path and parallel worktree split. | P0 | Done | Phase 0 | Org | BK-001 | docs/plans/ailit-compounding-knowledge-plan.md | Platform | Completed on 2026-05-06.
BK-003 | Foundation | Artifact Model | Define solution metadata contract | Create a stable structure for reusable solved-problem docs. | P0 | Done | Phase 1 | Org | BK-002 | docs/solutions/_template.md | Docs lane | Completed in the first artifact-model batch.
BK-004 | Foundation | Artifact Model | Create shared solution template and README | Give engineers a simple, repeatable way to store reusable solutions. | P0 | Done | Phase 1 | Org | BK-003 | docs/solutions/README.md | Docs lane | Completed in the first artifact-model batch.
BK-005 | Foundation | Documentation | Update docs to explain knowledge layers | Prevent confusion between standards, skills, solutions, decisions, and lessons. | P1 | Done | Phase 1 | Org | BK-003 | docs/skills.md | Docs lane | Overview and skills docs updated in the first artifact-model batch.
BK-006 | Registry | Solution Discovery | Add solution registry builder | Make solution docs searchable and loadable by the runtime. | P0 | Done | Phase 2 | Org | BK-004 | aios/solution_registry.py | Registry lane | Implemented with registry/solutions.json output.
BK-007 | Registry | Validation | Validate solution metadata and file shape | Keep shared knowledge high quality and predictable. | P0 | Done | Phase 2 | Org | BK-006 | registry/solutions.json | Registry lane | Validation now blocks invalid solution indexing.
BK-008 | Registry | CLI | Add list-solutions command | Let engineers inspect which reusable solutions are available. | P1 | Done | Phase 2 | Team | BK-006 | aios/cli.py | Registry lane | Implemented with plain output and JSON mode.
BK-009 | Registry | Search | Add search/filter support for solutions | Match solution docs by stack tags and problem keywords. | P1 | Done | Phase 2 | Team | BK-006 | aios/solution_registry.py | Registry lane | Implemented with query, status, and trust filters.
BK-010 | Capture | Knowledge Capture | Add capture-solution command | Turn solved work into a structured reusable solution note. | P0 | Done | Phase 3 | Team | BK-004, BK-006 | aios/capture_solution.py | Runtime lane | Implemented via CLI and shared solution document writer.
BK-011 | Capture | Promotion | Add promote-lesson command | Move good project lessons into shared reusable knowledge. | P0 | Done | Phase 3 | Team | BK-010 | aios/promote_lesson.py | Runtime lane | Implemented with lesson parsing from ai/lessons.md.
BK-012 | Capture | CLI | Add list-knowledge command | Give one place to inspect skills, solutions, and local knowledge artifacts. | P1 | Done | Phase 3 | Team | BK-006, BK-010 | aios/cli.py | Runtime lane | Implemented with optional project-local sections and JSON output.
BK-013 | Runtime | Prepare | Load matching solutions during prepare | Let the agent reuse proven solved patterns during task preparation. | P0 | Done | Phase 4 | Project | BK-006, BK-009 | aios/prepare.py | Runtime lane | Implemented with solution matching and context sections in prepare.
BK-014 | Runtime | Prompt Quality | Bound solution context size in prepare | Avoid token explosion when many matches exist. | P0 | Done | Phase 4 | Project | BK-013 | aios/context_builder.py | Runtime lane | Implemented with solution limits and excerpt truncation.
BK-015 | Runtime | Observability | Add runtime audit logging | Show whether AIlit was actually used during real tasks. | P1 | Done | Phase 4 | Org | BK-013 | aios/prepare.py | Runtime lane | Implemented with ai/usage.log entries from prepare.
BK-016 | Governance | Quality | Add trust and review status for shared knowledge | Shared knowledge should show whether it is draft or approved. | P1 | Done | Phase 5 | Org | BK-003, BK-006 | registry/solutions.json | Governance lane | Implemented with trust, review_status, reviewed_by, and last_reviewed.
BK-017 | Governance | Freshness | Detect stale or unreviewed solutions | Keep shared knowledge from decaying silently. | P2 | Done | Phase 5 | Org | BK-016 | aios/solution_registry.py | Governance lane | Implemented with age_days, is_stale, and list filters.
BK-018 | Testing | Registry Tests | Add tests for solution indexing and validation | Prevent registry regressions as the knowledge model grows. | P0 | Planned | Phase 2 | Org | BK-006, BK-007 | tests/ | QA lane | Need fixture solution docs.
BK-019 | Testing | Capture Tests | Add tests for capture and promotion commands | Keep post-work capture safe and predictable. | P0 | Planned | Phase 3 | Team | BK-010, BK-011 | tests/ | QA lane | Verify metadata mapping and filesystem output.
BK-020 | Testing | Runtime Tests | Add tests for prepare integration with solutions | Ensure runtime retrieval stays clean and bounded. | P0 | Planned | Phase 4 | Project | BK-013, BK-014 | tests/ | QA lane | Verify relevance ranking and output sections.
BK-021 | Rollout | Org Setup | Document shared team or org rollout model | Explain how to run one shared AIlit repo across many engineers and repos. | P1 | Done | Phase 5 | Org | BK-005 | docs/team_setup.md | Docs lane | Added team setup and governance guidance.

## Knowledge Model
Artifact Type | Purpose | Scope | Example Use
Standards | Stable reusable rules | Global or org | Engineering principles and approved rules
Skills | Reusable guidance modules | Global, team, or imported | How to approach a class of work
Solutions | Solved problem writeups | Shared team or org | How a real problem was solved and when to reuse it
Decisions | Project-local decision memory | Per project | Why a project chose a specific direction
Lessons | Project-local learnings | Per project | What was learned from recent work or incidents
Design rule | Do not force solved-problem writeups into skills. Solutions should remain a separate reusable knowledge type.

## Open Questions
ID | Question | Status | Current Direction | Owner
Q-001 | Where should reviewed shared solutions live long term? | Open | Use docs/solutions/ in the first pass. | Platform
Q-002 | How much of promotion should be automated? | Open | Start manual with good scaffolding and suggestions. | Platform
Q-003 | What is the minimum trust metadata for shared knowledge? | Open | Owner, source, review status, trust level, updated date. | Platform
Q-004 | How should stack-specific reusable patterns be tagged? | Open | Use simple tags first: language, framework, domain, infra. | Platform